## Sheet1
Phase | Task ID | Task Name | Assigned To | Estimated Start Date | Estimated End Date | Start Date | End Date | Duration (Days) | Effort (Hours/Per day) | Predecessor(s)
Initiation | 1 | Project Initiation and Scope Definition | Rashidul, Sawaira | 2025-03-25 | 2025-03-29 | 2025-03-25 | 2025-03-29 | 5 | 2
Requirements | 2 | Requirements Gathering and Analysis | Biruk, Sifan | 2025-03-26 | 2025-03-30 | 2025-03-26 | 2025-03-30 | 5 | 3 | 1
Requirements | 3 | Use Case Documentation (Booking System) | Sawaira | 2025-03-27 | 2025-04-01 | 2025-03-27 | 2025-04-01 | 6 | 3 | 2
Design | 4 | System Design (WBS, DFD, ERD) | Rashidul, Biruk, Sifan | 2025-03-28 | 2025-04-01 | 2025-03-28 | 2025-04-01 | 5 | 3 | 3
Design | 5 | Frontend Design for Booking UI | Sifan, Biruk, Sawaira | 2025-03-29 | 2025-04-02 | 2025-03-29 | 2025-04-02 | 5 | 3 | 4
Design | 6 | Backend API Design & Integration | Rashidul, Sawaira, Biruk | 2025-03-30 | 2025-04-04 | 2025-03-30 | 2025-04-04 | 6 | 4 | 4
Implementation | 7 | Testing & Debugging Booking Flow | Rashidul, Biruk, Sifan | 2025-03-31 | 2025-04-05 | 2025-03-31 | 2025-04-05 | 6 | 4 | 6
Implementation | 8 | Hotel Preference Optimization Algorithm | Rashidul, Sawaira, Biruk, Sifan | 2025-04-01 | 2025-04-06 | 2025-04-01 | 2025-04-06 | 6 | 3 | 5
Testing | 9 | System Evaluation & User Feedback | Biruk, Sifan | 2025-04-02 | 2025-04-08 | 2025-04-02 | 2025-04-08 | 7 | 2 | 8
Closure | 10 | Final Report and Presentation | Rashidul, Sawaira | 2025-04-03 | 2025-04-09 | 2025-04-03 | 2025-04-09 | 7 | 3 | 9