## Sheet1
ID | Requirement Description | Requested By | Category | Acceptance Criteria | Complexity | In Scope? | Test or Verification | Phase or Release
MA-015-02 | Enhance hotel booking system to minimize overbookings and ensure real-time availability. |  | Technology Optimization | Integration between hotel, ride, and dining systems must be seamless. | High | Yes | Test real-time hotel booking updates and availability. | Phase 1
MA-015-03 | Optimize ride reservation system to reduce wait times and ensure equitable access to attractions. |  | Guest Experience Enhancement | The ride reservation system should dynamically adjust to real-time data. | High | Yes | Test ride reservation system to ensure fair guest access. | Phase 1
MA-015-04 | Improve data integration between hotel bookings, ride reservations, and guest services. |  | Technology Optimization | All systems (hotel, rides, dining) should be interconnected and update in real-time. | High | Yes | Verify data flows between hotel, ride, and dining systems. | Phase 2
MA-015-05 | AI-based personalization for guest experience, including tailored ride, hotel, and dining recommendations. |  | Guest Experience Enhancement | Recommendations should be based on AI algorithms using prior guest preferences. | High | Yes | Test AI recommendation system for accurate and personalized suggestions. | Phase 2
MA-015-06 | Implement biometric authentication (e.g., facial recognition) for hotel check-in, park entry, and ride access to streamline guest verification and enhance security. | Project Team | Security & Access | Biometric login and park access must be functional for registered guests; tested with sample guest profiles. | High | Yes | Verify biometric system login, entry scans, and error handling. | Phase 2
MA-015-07 | Deploy a real-time notification and alert system to inform guests about ride availability, schedule changes, and personalized recommendations. | Project Team | Guest Communication | Notifications must be delivered in-app based on user preferences and system events. | Medium | Yes | Test delivery of ride availability and itinerary alerts. | Phase 2
MA-015-08 | Integrate sustainability features such as digital ticketing, refillable water station alerts, and guest rewards for eco-friendly behavior. | Project Team | Sustainability | System must provide digital-first options and reward tracking features. | Medium | Yes | Verify guest actions are logged and tracked toward sustainability rewards. | Phase 3
MA-015-09 | Enhance mobile app accessibility through multi-language support, screen reader compatibility, and visual assistance features. | Project Team | Accessibility | All app features must support multi-language settings and WCAG 2.1 accessibility standards. | Medium | Yes | Test app in various languages and with accessibility tools (e.g., screen readers). | Phase 3
MA-015-10 | Redesign the mobile app interface for improved user experience with simplified navigation, contextual help, and adaptive layouts. | Project Team | User Experience | Users should complete key tasks 20% faster in usability testing compared to previous version. | Medium | Yes | Conduct usability testing and compare task completion time and satisfaction ratings. | Phase 1
MA-015-11 | Implement advanced data security features, including encryption, anomaly detection, and compliance with GDPR and CCPA. | Project Team | Security & Compliance | All user data should be encrypted at rest and in transit; logs must track access and flag anomalies. | High | Yes | Penetration testing and security audit for compliance and breach prevention. | Phase 3
MA-015-12 | Ensure WCAG 2.1 AA compliance for all mobile app pages accessed by guests, including color contrast, alt text for images, and resizable text. | Project Team | Accessibility | All screens must pass automated and manual WCAG 2.1 AA checks. | Medium | Yes | Conduct accessibility audits using tools like WAVE and manual keyboard-only navigation. | Phase 2
MA-015-13 | Add screen reader compatibility for all navigational elements, forms, and alerts in the mobile application. | Project Team | Accessibility | Screen readers must read all focusable elements accurately in the correct order. | Medium | Yes | Verify with JAWS, NVDA, or VoiceOver screen readers. | Phase 2
MA-015-14 | Support localization by providing multi-language UI options for major guest languages (e.g., Spanish, Mandarin, French). | Project Team | Localization | All UI text and guest communication should switch based on selected language preference. | Medium | Yes | Verify complete language switching using multilingual guest profiles. | Phase 3