## Sheet1
Risk | Probability 0 (Not Probable) 5 (Highly Probable) | Impact 0 (Low Impact) 5 (High Impact) | Priority | Mitigation Plan
System Downtime or Technical Glitches during Peak Load | 4 | 5 | High | Use a cloud-based scalable architecture with load balancing and conduct frequent stress tests.
Data Breach or Security Vulnerability | 3 | 5 | High | Enable encryption, multi-factor authentication, and conduct regular security assessments. Ensure GDPR and CCPA compliance.
Miscommunication between Subsystems (Hotel, Rides, Dining) | 3 | 4 | Medium | Integrate systems using a centralised database and standard APIs. Include automated data synchronisation.
Guest Confusion with New App Features | 4 | 3 | Medium | Implement contextual guidance, onboarding training, and streamlined UI/UX testing. Offer live help channels.
Accessibility and Inclusion Oversight | 2 | 4 | Medium | Conduct usability testing with a varied group of users. Follow the WCAG 2.1 accessibility criteria properly.
AI Recommendations Deliver Irrelevant Results | 3 | 3 | Medium | Continuously retrain the recommendation engine based on guest comments and behaviour data. Add manual override options.
Project Timeline Delays due to Team Coordination or Scope Creep | 2 | 4 | Medium | Use a project schedule (such as a Gantt chart). Assign defined responsibilities and track progress weekly.
Resistance from Non-Tech-Savvy Users | 3 | 3 | Medium | Ensure that alternate traditional services (guest desks, printed maps) are available alongside digital services.
Missed Deadlines by Third-Party Vendor (Project Risk) | 3 | 4 | High | Establish contractual deadlines with penalties, maintain buffer time in the schedule, and conduct regular status check-ins with vendors.
Lack of Availability of Key Personnel (Project Risk) | 4 | 4 | High | Cross-train team members and maintain a backup resource pool to reduce reliance on single individuals.
Unclear or Incomplete Requirements (Project Risk) | 3 | 4 | High | Conduct thorough stakeholder interviews, iterative reviews, and maintain a dynamic requirements document with regular validations.
Incorrect Data Schema Design (System Risk) | 3 | 5 | High | Review schema with both developers and domain experts, perform unit testing on data mapping, and validate with real scenarios.
Inaccurate Growth Projections (System Risk) | 4 | 4 | High | Model system using scalable infrastructure; regularly revisit forecasts with updated usage data and plan for high elasticity in system capacity.